## Summary
New to the Hotlist | Supplier Name | DoH SoH Weeks of cover | Orders with suppliers | Supplier SoH | Supp QA | Aug-2022 Pipeline | Sep-2022 Pipeline | Oct-2022 Pipeline | Latest Contract Manager comments
Chlorphenamine; 2mg/5ml; Syrup; 50 ml | Adcock Ingram Healthcare (Pty) Ltd | 4.7266 | 637050 | 266132 | 153200 | 125000 | 720000 | 875000 | Supplier is expecting stock end of August, NCL issued
Paracetamol; 120mg/5ml; Syrup; 50 ml | Barrs Pharmaceuticals Industries (pty) Ltd | 5.6123 | 1448085 | 0 | 100000 | 650000 | 650000 | 500000 | partial deliveries are done
Zinc Oxide, Castor Oil; Ointment; 25 g | Barrs Pharmaceuticals Industries (pty) Ltd | 5.352 | 357526 | 9454 | 20000 | 120000 | 120000 | 120000 | shortage of cetosteryl alcohol, partial deliveries, NCL issued, partial deliveries
Brimonidine; 2mg/ml; Drop, Eye; 5 ml | Actor Pharma (pty) Ltd | 5.873 | 3724 | 1526 | 0 | 0 | 15000 | 0 | High demand and supply has exceeded contractual demand, Demand Planning is looking at the usage and demand forecast. There is stock on hand for partial deliveries and 15000 units expected in Sep
Warfarin; 5mg; Tablet; 100 Tablets | Cipla Medpro SA (Pty) Ltd | 5.1917 | 73319 | 0 | 0 | 48000 | 32000 | 70000 | 13 700 units arrived on Tuesday and was sent to QA yesterday Allocations have been done and Circular sent out to Provinces to place new orders for the 28 pack size for July and August.
Longer term Hotlist item
Lactulose; 3.35g/5ml; Syrup; 150 ml | Pharmacare Limited | 5.2723 | 252446 | 4185 | 0 | 75000 | 100000 | 100000 | Production delays, and normal supply to resume in Dec. 75000 units expected end Aug and 100000 units in Sep.
Beclometasone; 50mcg; Spray, Nasal; 150 Doses | Cipla Medpro SA (Pty) Ltd | 3.4766 | 19878 | 0 | 0 | 60000 | 110000 | 0 | 60 000 units expected in August and 110 000 units for September. Demand exceeds the forecast for item.
Sodium Bicarbonate; 8.5%; injection; 50 ml | FRESENIUS KABI SOUTH AFRICA (PTY) LTD | 3.326 | 59428 | 0 | 2730 | 0 | 38200 | 28650 | was a delay in packaging material, stock will be released second week of July, stock was released
Povidone Iodine; 10%; Liquid; 1 L | Barrs Pharmaceuticals Industries (pty) Ltd | 4.1281 | 80331 | 1500 | 0 | 20000 | 20000 | 20000 | partial deliveries are done
Calcium Carbonate, Glycine; 420mg, 180mg; Tablet; 168 Tablets | Evohealth (Pty) Ltd | 5.0118 | 6500 | 0 | 0 | 5000 | 0 | 51200 | Delay in manufacturing, stock will be available end of August
Amitriptyline; 25mg; Tablet; 56 Tablets | Pharmacare Limited | 5.062 | 16860 | 0 | 0 | 57142 | 0 | 57142 | Partial deliveries. 57414 units expected in Aug should clear all the back orders.
Olanzapine; 5mg; Tablet; 28 Tablets | RANBAXY PHARMACEUTICALS (PTY) LTD | 4.4037 | 57336 | 23654 | 0 | 11030 | 11030 | 11030 | Had a delay in manufacturing. Some backorders cleared with July stock recieved, more stock expected August. Ranbaxy has a lot of stock of the Olanzapine 2.5mg tablets as an alternative. New PAT report not yet uploaded this week.
Paracetamol; 120mg/5ml; Syrup; 500 ml | Barrs Pharmaceuticals Industries (pty) Ltd | 3.4343 | 44215 | 0 | 10000 | 15000 | 15000 | 15000 | Suppliers production was delayed due to the increase of the API price, and 4 month delay from the API manufacturers,supplier is catching up with orders, some orders are from NW- account on hold NCL was issued, partial deliveries - PPQ sent to the provinces
Levodopa, Carbidopa; 100mg, 25mg; Tablet; 100 Tablets | RANBAXY PHARMACEUTICALS (PTY) LTD | 5.2864 | 23421 | 5700 | 0 | 5575 | 5575 | 5575 | Some stock awaiting QA release and more stock expected in August. This will clear at least 67% of the backorder.
Calcium Carbonate; 500mg; Tablet; 10 Tablets | Evohealth (Pty) Ltd | 3.7721 | 12000 | 102 | 0 | 20000 | 20000 | 195000 | Delay in manufacturing, stock will be available end of August
Betamethasone; 500mcg; Tablet; 20 Tablets | Pharmacare Limited | 0.48148 | 78 | 0 | 0 | 0 | 0 | 0 | Section 21 in progress
Glibenclamide; 5mg; Tablet; 84 Tablets | Biotech Laboratories (Pty) Ltd | 5.344 | 28750 | 0 | 0 | 0 | 47000 | 23000 | 47 000 units expected end August. All backorders were cleared with stock in QA. Current order in the system for 28 750 units. Biotech has stock of the 56 pack size.
Carvedilol; 25mg; Tablet; 30 Tablets | Cipla Medpro SA (Pty) Ltd | 4.992 | 212675 | 0 | 0 | 60000 | 270000 | 120000 | 60 000 units expected end of August and another 270 000 in September. Non-compliance letter issued for this item.
Betamethasone; 500mcg; Tablet; 100 Tablets | Pharmacare Limited | 0 | 755 | 0 | 0 | 0 | 0 | 0 | Section 21 in progress
Povidone Iodine; 1%; Liquid; 100 ml | Barrs Pharmaceuticals Industries (pty) Ltd | 2.1696 | 19540 | 0 | 15000 | 5000 | 5000 | 5000 | partial deliveries are done
Hydrocortisone; 1%; Cream; 20 g | Barrs Pharmaceuticals Industries (pty) Ltd | 4.0214 | 697377 | 11402 | 0 | 50000 | 50000 | 150000 | shortage of cetosteryl alcohol, partial deliveries, NCL issued, supplier is catching up with orders- RFQ sent out to the maerket. PPQ sent out
Betamethasone Valerate; 0.1%; Cream; 50 g | Barrs Pharmaceuticals Industries (pty) Ltd | 4.7346 | 110364 | 0 | 10000 | 20000 | 20000 | 20000 | RFQ sent out to the market
Povidone Iodine; 10%; Ointment; 25 g | Barrs Pharmaceuticals Industries (pty) Ltd | 4.3762 | 213094 | 0 | 20000 | 80000 | 80000 | 80000 | NCL., partial deliveries
Moxifloxacin; 400mg; Tablet; 28 Tablets | Macleods Pharmaceuticals SA (Pty) Ltd | 4.7922 | 5265 | 0 | 0 | 1300 | 0 | 0 | 1 300 units scheduled for August. No response from Macleods. Non-compliance letter to be issued.
Metronidazole; 400mg; Tablet; 100 Tablets | Innovata Pharmaceuticals (Pty) Ltd | 5.736 | 6376 | 1210 | 2000 | 6000 | 6000 | 6000 | Stock in QA. There's 4000 units expected in Aug.
Imipenem, Cilastatin; 500mg, 500mg; injection; 1 Injection | RANBAXY PHARMACEUTICALS (PTY) LTD | 4.3512 | 78053 | 0 | 23809 | 11477 | 11477 | 11477 | 50 000 was expected end of July to clear 85% of the backorder. No PAT report uploaded as yet for this week.
Moxifloxacin; 400mg; Tablet; 10 Tablets | Macleods Pharmaceuticals SA (Pty) Ltd | 2.9387 | 2261 | 0 | 0 | 1200 | 0 | 5000 | 1200 units scheduled for August and another 5 000 for October. Non-compliance letter to be issued.
Cefepime; 1g; injection; 1 Injection | Aurobindo Pharma (Pty) Ltd | 5.2753 | 3040 | 0 | 0 | 0 | 0 | 0 | Short dated stock is available, fresh stock will be available end of August
Water For Irrigation; Liquid (Pour Water); 1 L | B Braun Medical (pty) Ltd | 5.4843 | 229270 | 6530 | 212200 | 150000 | 400000 | 400000 | Backordes will be cleared with stock in QA and stock manufactured in August.
Sodium Chloride; 0.9%; Infusion (parenteral); 200 ml | B Braun Medical (pty) Ltd | 4.6899 | 1101378 | 52128 | 155016 | 486000 | 324000 | 432000 | Stock delivered on allocation basis. Meeting monthly demand. All backorders should be cleared by end September.
Cyproterone; 50mg; Tablet; 20 Tablets | Cipla Medpro SA (Pty) Ltd | 2.3823 | 38790 | 0 | 0 | 0 | 0 | 0 | API shortage, not available from Bayer on buy out either. Non-EML item. Circular was sent out to Provinces on therapeutic alternatives to use. Supply to commence in October.
Sodium Chloride; 0.9%; Infusion (parenteral); 50 ml | B Braun Medical (pty) Ltd | 4.7081 | 944172 | 12600 | 384696 | 400000 | 400000 | 400000 | Stock delivered on allocation basis. Meeting monthly demand. All backorders should be cleared by end September.
Hydrocortisone; 1%; Ointment; 25 g | Pharmacare Limited | 5.0122 | 299145 | 60000 | 0 | 50000 | 50000 | 0 | NCL given. Production delays. There 310000 units expected between Aug and Dec. Normal supply expected to resume in Jan 2023.
Change in Demand Plan
Possible changes to
No longer on the Hotlist
Benzyl Benzoate; 25%; Liquid; 100 ml | Barrs Pharmaceuticals Industries (pty) Ltd | 5.5107 | 58000 | 200008 | 0 | 20000 | 20000 | 50000 | Partial deliveries are made until the one of the ingredients is back in stock by end of February
Losartan; 100mg; Tablet; 28 Tablets | Austell Pharmaceuticals (Pty) Ltd | 4.592 | 1540 | 27323 | 0 | 0 | 177856 | 0 | partial deliveries are done
Metoclopramide; 5mg/5ml; Syrup; 100 ml | Pharmacare Limited | 7.9742 | 24998 | 0 | 0 | 9000 | 18000 | 0 | Demand is higher than anticipated. Doing partial deliveries and back orders expected to be cleared in September.